## Execution Plan
Task | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | Owner | Date Completed
Finalize scaled SFE (1–5A) | 2026-01-26: Done | Kim | 2026-01-22
Finalize signal conditioning | 2026-01-26: Done | Lawson | 2026-01-22
Firmware DSP → JSON pipeline | 2026-01-26: Done | Caiden | 2026-01-23
App live telemetry display | 2026-01-26: In Progress; 2026-02-02: In Progress; 2026-02-09: In Progress; 2026-02-16: In Progress; 2026-02-23: Done | Vivek | 2026-02-20
PCB bring-up & bench validation | 2026-01-26: In Progress; 2026-02-02: In Progress; 2026-02-09: In Progress; 2026-02-16: In Progress; 2026-02-23: Behind | Kim, Lawson, Caiden
ML inference integration | 2026-02-02: In Progress; 2026-02-09: In Progress; 2026-02-16: In Progress; 2026-02-23: Done | Joshua | 2026-02-20
End-to-end system integration | 2026-02-23: Behind | Full Team
System-level validation | [11 empty] | Full Team
Stress & endurance testing | [11 empty] | Full Team
Final demo prep + documentation | [11 empty] | Full Team
ML inference integration
Task | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | Owner | Date Completed
Finalize scaled SFE (1–5A) | 2026-01-26: Done | Kim | 2026-01-22
Finalize signal conditioning | 2026-01-26: Done | Lawson | 2026-01-22
Firmware DSP → JSON pipeline | 2026-01-26: Done | Caiden | 2026-01-23
App live telemetry display | 2026-01-26: In Progress; 2026-02-02: In Progress; 2026-02-09: In Progress; 2026-02-16: In Progress; 2026-02-23: Done | Vivek | 2026-02-20
PCB bring-up & bench validation | In Progress | In Progress | In Progress | In Progress | Behind | Behind | Done |  |  |  |  | Kim, Lawson, Caiden | 2026-03-09
ML inference integration | 2026-02-02: In Progress; 2026-02-09: In Progress; 2026-02-16: In Progress; 2026-02-23: Done | Joshua | 2026-02-20
End-to-end system integration | 2026-02-23: Behind; 2026-03-02: Behind; 2026-03-09: Done | Full Team | 2026-03-09
System-level validation | 2026-03-09: In Progress; 2026-03-16: In Progress; 2026-03-23: In Progress; 2026-03-30: In Progress; 2026-04-06: Done | Full Team | 2026-04-01
Stress & endurance testing | 2026-03-09: In Progress; 2026-03-16: In Progress; 2026-03-23: In Progress; 2026-03-30: In Progress; 2026-04-06: Done | Full Team | 2026-04-01
Final demo prep + documentation | 2026-04-06: Done | Full Team | 2026-04-20